## EXECUTIVE SUMMARY
EXECUTIVE SUMMARY - LATROBE FINANCIAL
3 NIELD AVENUE, BALGOWLAH - TOWNHOUSE DEVELOPMENT
2025-09-13
LOAN STRUCTURE |  |  | SECURITY & LVR
Loan Amount: | 8727273 |  | On Completion Value: | On Completion Value: | 11772727.2727
Interest Rate: | 8.39% p.a. |  | Land Value: | Land Value: | 4000000
Loan Term: | 15 months |  | LVR (Land): | LVR (Land): | 45.83%
Monthly Interest: | $23000 - $62000 |  | LVR (Completion): | LVR (Completion): | 74.13%
Total Interest: | 593036.7551 |  | Loan to Cost: | Loan to Cost: | 80%
DEVELOPMENT OVERVIEW |  |  | EXIT STRATEGY
Property Type: | 2 Luxury Townhouses |  | Sale Timing: | Sale Timing: | At Structure Complete
Total Internal Area: | 659.54 m² |  | Expected Sale Price: |  | 14445401.25
Construction GBA: | 788.11 m² |  | Sale Rate per m²: |  | 23798.0251
Construction Cost: | 5018581.8725 |  | Net Profit (Pre-tax): |  | 643823.6151
Contingency (10%): | 472058.1872 |  | ROI (Pre-tax): |  | 50.23%
PAYMENT SCHEDULE
Month | Period | Progress / Milestone | Draw | Interest | Cumulative
1 | Oct 2025 | Site prep & excavation | 300000 | 23268 | 300000
2 | Nov 2025 | Footings & foundation | 420000 | 28079 | 720000
3 | Dec 2025 | Slab complete | 420000 | 33164 | 1140000
4 | Jan 2026 | Frame stage commence | 420000 | 36785 | 1560000
5 | Feb 2026 | Frame stage | 420000 | 42293 | 1980000
6 | Mar 2026 | Roof & external walls | 420000 | 46442 | 2400000
7 | Apr 2026 | Windows & lock-up | 379000 | 44696 | 2779000
8 | May 2026 | Internal walls & plumbing | 420000 | 53912 | 3199000
9 | Jun 2026 | Electrical & insulation | 406000 | 55385 | 3605000
10 | Jul 2026 | Plaster & internal linings | 420000 | 60801 | 4025000
11 | Aug 2026 | Kitchen & bathrooms | 406000 | 61409 | 4431000
12 | Sep 2026 | Flooring & painting | 420000 | 65521 | 4851000
13 | Oct 2026 | Final fit-out & completion | 406000 | 63417 | 5257000
0 | TOTAL | Construction Complete | 5257000 | 615172 | 5257000
0
KEY STRENGTHS |  |  | RISK MITIGATION
✓ Conservative LVR structure (45.83% land, 75% completion) |  |  | • Fixed price construction contract
✓ Monthly interest payments demonstrate strong cash flow |  |  | • S-curve progress payments aligned to milestones
✓ 10% construction contingency ($454,709) |  |  | • No reliance on pre-sales
✓ Proven location with recent comparable sales |  |  | • Value engineering savings incorporated
✓ Flexible exit strategy at structure complete |  |  | • Experienced developer/builder team
0
CONTACT INFORMATION
Developer: | Johinke Developments |  | Broker: | [Broker Name]
Phone: | [Phone Number] |  | Email: | [Email Address]
Note: Full financial model and supporting documentation available upon request

## FEASABILITY STUDY
3 Nield Avenue Balgowlah - Feasibility |  |  |  |  | 2025-09-12 | 25
DESCRIPTION | QUANTITY | UNIT | RATE | AMOUNT | DEBIT | CREDIT
TOWNHOUSE COMPARISONS
156a Woodland Street (19 Oct 2021) | 258 | m2 | 16531.0078 | 4265000 |  | 4265000
156a Woodland Street (15 May 2024 - Core Logic) | 258 | m2 | 17151.1628 | 4425000 |  | 4425000
2/148 Woodland Street (23 Feb 23) | 255 | m2 | 18529.4118 | 4725000 |  | 4725000
25 Nield Avenue (26 Sep 23) | 242 | m2 | 19628.0992 | 4750000 |  | 4750000
53a Seaview Street (04 Jun 23) | 285 | m2 | 20701.7544 | 5900000 |  | 5900000
18 Willyama Avenue (For Sale) | 285 | m2 | 28771.9298 | 8200000 |  | 8200000
25 NIELD AVE BALGOLWAH (26 SEP 2023) - Actual | 319 | m2 | 14890.2821 | 4750000 |  | 4750000
Land Value | 1 | LS | 1920000 | 1920000 |  | 1920000
Improved Land Value | 1 | LS | 2830000 | 2830000 |  | 2830000
Lift Improvement | 1 | LS | 250000 | 250000 |  | 250000
Pool Improvement | 1 | LS | 300000 | 300000 |  | 300000
Away from Main Road | 1 | LS | 250000 | 250000 |  | 250000
15m Width Vs 20m Width | 1 | LS | 200000 | 250000 | -250000
Larger Internal | 36.27% | % | 3380000 | 1225878.5124 |  | 1225878.5124
Increased Land Size | 4.248% | % | 1920000 | 81568.6275 |  | 81568.6275
Increase Property Prices to 29 May 2025 | 3% | % | 6857447.1398 | 205723.4142 |  | 205723.4142
Therefore with Improvements | 319 | m2 | 21496.6995 | 6857447.1398 |  | 6857447.1398
3 Nield Ave Using Adjustments Rate above | 306 | m2 | 21496.6995 | 13670617.6939 | -250000 | 13920617.6939
53A SEAVIEW STREET BALGOWLAH (09 April 2025) - Actual | 339 | m2 | 17404.1298 | 5900000 |  | 5900000
Land Value | 1 | LS | 2770000 | 2770000 |  | 2770000
Improved Land Value | 1 | LS | 3130000 | 3130000 |  | 3130000
Distant Views - No Tree | 1 | LS | 250000 | 300000 |  | 350000
Away from Main Road Improvement | 1 | LS | 250000 | 250000 |  | 250000
Larger Internal | 15.71% | % | 3130000 | 491684.5614 |  | 491684.5614
Increased Land Size | 10.78% | m% | 2770000 | 298725.4902 |  | 298725.4902
Therefore with Improvements | 339 | m2 | 21505.6344 | 7290410.0516 |  | 7290410.0516
3 Nield Ave Using Adjustments Rate above | 306 | m2 | 21505.6344 | 6580724.1174 | 0 | 7290410.0516
18 WILLYAMA AVE FAIRLIGHT (04 June 2025) - For Sale | 323 | m2 | 23839.0093 | 7700000 |  | 7700000
Land Value | 1 | LS | 2075000 | 2075000 |  | 2075000
Improved Land Value | 1 | LS | 5625000 | 5625000 |  | 5625000
Better Views | 1 | LS | 900000 | 750000 | -750000
16m Width Vs 20m Width | 1 | LS | 200000 | 250000 | -250000
Fairlight Postcode | 1 | LS | 400000 | 450000 | -450000
Larger Internal | 15.71% | % | 4175000 | 655841.2281 |  | 655841.2281
Increased Land Size | 5.556% | m% | 5625000 | 312500 |  | 312500
Therefore with Improvements | 323 | m2 | 22347.8057 | 7218341.2281 |  | 7218341.2281
3 Nield Ave Using Adjustments Rate above | 306 | m2 | 22347.8057 | 6838428.5319 | -1450000 | 15886682.4561
3 NIELD AVE BALGOWLAH (29 May 2025) - Valuation 6 May 2025 | 607 | m2 | 21334.4316 | 12950000 |  | 12950000
Land Value | 1 | LS | 4000000 | 4000000 |  | 4000000
New Improved Land Value | 2 | LS | 4475000 | 8950000 |  | 8950000
Conservative Valuation Adjustment | 4.25% | % | 13500375 | 550375 |  | 550375
Additional Value till Sale (Prediction 3-4 Rate Drops 2025/26 Since Valuation) | 7% | % | 13500375 | 945026.25 |  | 945026.25
Therefore with Improvements (+ % during Construction) | 607 | m2 | 23798.0251 | 14445401.25 | 0 | 14445401.25
7%
TOWNHOUSE A - MAR 2024 - Estimate - Internal Area | 306 | m2 | 23798.0251 | 7282195.6878 |  | 7282195.6878
TOWNHOUSE B - MAR 2024 - Estimate - Internal Area | 301 | m2 | 23798.0251 | 7163205.5622 |  | 7163205.5622
SUBTOTAL | 607 | m2 | 23798.0251 | 14445401.25 | 0 | 14445401.25
7%
TOWNHOUSE A - MAR 2024 - Estimate - Internal Area | 333.84 | m2 | 21902.2368 | 7311842.7287 |  | 7311842.7287
TOWNHOUSE B - MAR 2024 - Estimate - Internal Area | 325.7 | m2 | 21902.2368 | 7133558.5213 |  | 7133558.5213
SUBTOTAL | 659.54 | m2 | 21902.2368 | 14445401.25 | 0 | 14445401.25
OFFICES & EXPENSES
OFFICE - 15% | 15% | % | 89168.5912 | 13375.2887 | -13375.2887
ELECTRICITY - 15% | 15% | % | 10000 | 1500 | -1500
WATER - 15% | 15% | % | 2000 | 300 | -300
GAS - 15% | 15% | % | 2000 | 300 | -300
INTERNET - 80% | 80% | % | 2702.0785 | 2161.6628 | -2161.6628
MOBILE PHONES - IPHONES / PADS - 80% | 80% | % | 13106.2356 | 10484.9885 | -10484.9885
CAR - FORD RANGER - 80% | 80% | % | 120000 | 96000 | -96000
PRINTER & CONSUMABLES - 80% | 80% | % | 2000 | 1600 | -1600
LAPTOPS - 100% | 100% | % | 4000 | 4000 | -4000
MICROSOFT OFFICE - 100% | 100% | % | 20265.5889 | 20265.5889 | -20265.5889
MEETINGS - DINNERS, SITE VISITS - 100% | 100% | % | 20000 | 20000 | -20000
WEBSITE PROVIDER (GO DADDY) - 100% | 100% | % | 500 | 500 | -500
ANNUAL SUBSCRIPTION CHATGPT PRO - 80% | 80% | % | 7200 | 5760 | -5760
ANNUAL SUBSCRIPTION COPILOT - 100% | 100% | % | 240 | 240 | -240
ANNUAL SUBSCRIPTION ARCHISTAR - 100% | 100% | % | 1440 | 1440 | -1440
ANNUAL SUBSCRIPTION PROPCODE - 100% | 100% | % | 1100 | 1100 | -1100
ANNUAL SUBSCRIPTION CORELOGIC PROPERTY VALUE - 100% | 100% | % | 900 | 900 | -900
ANNUAL SUBSCRIPTION ENGINEERS AUSTRALIA - 100% | 100% | % | 750 | 750 | -750
ANNUAL SUBSCRIPTION - GITHUB - 100% | 100% | % | 1000 | 1000 | -1000
SUBTOTAL | 27 | Mths | 6166.7496 | 166502.2402 | -166502.2402 | 0
DEVELOPER CDC & MISCELLANEOUS COST
TRUST ESTABLISHMENT | 1 | LS | 3000 | 3000 | -3000
ARCHITECTURAL CONSULTANT | 1 | LS | 60000 | 60000 | -60000
ARCHITECTURAL REDESIGN | 1 | LS | 15000 | 15000 | -15000
STRUCTURE CONSULTANT | 1 | LS | 7500 | 7500 | -7500
STRUCTURE REDESIGN | 1 | LS | 3750 | 3750 | -3750
STORMWATER CONSULTANT | 1 | LS | 2000 | 2000 | -2000
SECTION 73 CONSULTANT | 1 | LS | 5000 | 5000 | -5000
SYDNEY WATER TAP-IN | 1 | LS | 151.3 | 151.3 | -151.3
BASIX CONSULTANT | 1 | LS | 1254 | 1254 | -1254
LANDSCAPE CONSULTANT | 1 | LS | 1430 | 1430 | -1430
TOWN PLANNING CONSULTANT | 1 | LS | 5000 | 5000 | -5000
PCA | 1 | LS | 13850 | 13850 | -13850
PLANNING ADVICE | 1 | LS | 2000 | 2000 | -2000
SURVEYOR | 1 | LS | 1400 | 1400 | -1400
SURVEYOR ADDITIONAL | 1 | LS | 500 | 500 | -500
MARKETING RENDERS | 1 | LS | 9350 | 9350 | -9350
GEOTECH - EXCAVATION, ACID SULFATE & GROUND REPORT | 1 | LS | 1045 | 1045 | -1045
CIVIL ENGINEER | 1 | LS | 4015 | 4015 | -4015
SELLING AGENT MARKETING | 1 | LS | 13000 | 13000 | -13000
LONG SERVICE LEVY | 0.25% | LS | 1701800 | 4254.5 | -4254.5
PROPERTY VALUATION | 2 | LS | 2500 | 5000 | -5000
SUBTOTAL | 659.54 | m2 | 240.3187 | 158499.8 | -158499.8 | 0
LAND TAX
LAND VALUE - NO THRESHOLD DUE TO BEING A TRUST | 0% | % | 2530000 | 0
LAND TAX - DECEMBER 2025 (IICL LATE BILL) | 1.6% | % | 2530000 | 40580 | -40580
LAND TAX - DECEMBER 2025 | 1.6% | % | 2530000 | 40580 | -40580
SUBTOTAL | 3.208% | % | 2530000 | 81160 | -81160 | 0
BUYERS AGENT
SUBTOTAL | 0.624% | % | 4808000 | 30000 | -30000 | 0
COUNCIL COST
SECTION 7.11 CONTRIBUTIONS | 2 | UNIT | 20000 | 40000 | -40000
SUBTOTAL | 2 | UNIT | 20000 | 40000 | -40000 | 0
DEVELOPER PURCHASE FINANCE - 70 LVR COST
FINANCE AMOUNT | 70% | % | 4808000 | 3365600
APPLICATION FEE + GST | 1.25% | % | 3365600 | 42070 | -42070
MANDATE FEE + BROKERS COMM + GST | 1.8% | % | 3365600 | 60580.8 | -60580.8
INTEREST - (PRE CONSTRUCTION) | 10.1% | % | 3365600 | 339778.0668 | -339778.0668
ACCOUNT FEE - 12 MONTH (PRE CONSTRUCTION) | 0.03565% | % | 3365600 | 1200 | -1200
LAWYERS FEE HWL | 0.1078% | % | 3365600 | 3628.47 | -3628.47
SUBTOTAL | 13.29% | % | 3365600 | 447257.3368 | -447257.3368 | 0
DEVELOPER INCOME RENTAL
RENTAL RETURN | 49 | Wks | 2450 | 120050 |  | 120050
REAL ESTATE FEES | 15% | % | 120050 | 18007.5 | -18007.5
SUBTOTAL | 49 | Wks | 2082.5 | 102042.5 | -18007.5 | 120050
RECENT SALES - NIELD AVE BALGOWLAH
9 Nield Avenue (15 May 2024 - Core Logic) | 601 | m2 | 6239.6007 | 3750000
17 Nield Avenue (15 May 2024 - Core Logic) | 418 | m2 | 9569.378 | 4000000
AVERAGE PRICE | 607 | m2 | 7904.4893 | 4798025.0221
DEVELOPER ACTUAL COST PURCHASE VALUE - 70 LVR COST
PURCHASE PRICE - FLOOR AREA RATE | 607 | m2 | 7920.9226 | 4808000
CASH DEPOSIT (10%) | 10% | % | 4808000 | 480800 | -480800
CASH (20%) | 20% | % | 4808000 | 961600 | -961600
LOAN (70%) | 70% | % | 4808000 | 3365600 | -3365600
STAMP DUTY | 607 | m2 | 436.1984 | 264772.4 | -264772.4
REGISTRATION FEE | 1 | LS | 515 | 515 | -515
SETTLEMENT FEE | 1 | LS | 137.39 | 137.39 | -137.39
LAWYERS FEE - TG LAW | 1 | LS | 3628.47 | 3628.47 | -3628.47
COUNCIL FEES | 1 | LS | 3204.37 | 3204.37 | -3204.37
SUBTOTAL | 607 | m2 | 8369.4524 | 5080257.63 | -5080257.63 | 0
BUILDER CONSTRUCTION COST (EXCL GST)
TOWNHOUSE A - Nov 2024 - Estimate (25 Nield Avenue) GBA | 399.95 | m2
TOWNHOUSE B - Nov 2024 - Estimate (25 Nield Avenue) GBA | 388.16 | m2
CONSTRUCTION COST | 788.11 | m2 | 6305 | 4969033.55 | -4969033.55
VALUE ENGINEERING | 5% | % | 4969033.55 | 248451.6775 |  | 248451.6775
CONSTRUCTION COST PROFIT (BUILDER INVESTED) | 0% | % | 4720581.8725 | 0 | 0
CONTINGENCY | 10% |  | 4720581.8725 | 472058.1872 | -472058.1872
VARIATION 1 - CONSULTANTS | 1 | LS | 90000 | 90000 | -90000
VARIATION 2 - CONNECTION SERVICES - POWER / WATER / SEWER / STORMWATER | 6 | LS | 5000 | 30000 | -30000
VARIATION 3 - JOINERY | 2 | LS | 25000 | 50000 | -50000
VARIATION 4 - SOLAR PANELS | 2 | LS | 15000 | 30000 | -30000
VARIATION 5 - SOLAR BATTERY & INVERTER | 2 | LS | 10000 | 20000 | -20000
VARIATION 6 - UNDERTILE HEATING | 6 | LS | 3000 | 18000 | -18000
VARIATION 7 - HYDRAULIC POOL BASE | 2 | LS | 30000 | 60000 | -60000
SUBTOTAL | 788.11 | m2 | 6966.8448 | 5490640.0598 | -5739091.7373 | 248451.6775
75%
VALUATION | 607 | m2 | 19170.2861 | 11636363.6364
MAXIMUM FINANCE AMOUNT | 75% | % | 11636363.6364 | 8727272.7273
DEVELOPMENT LOAN | 75% | % | 11636363.6364 | 8727272.7273
APPLICATION FEE | 1.25% | % | 8727272.7273 | 109090.9091 | -109090.9091
LAWYERS + DISBURSTMENTS | 0.02113% | % | 8727272.7273 | 1844.5 | -1844.5
MANDATE FEE + BROKERS COMMISSON | 0.5% | % | 8727272.7273 | 43636.3636 | -43636.3636
QS FEES | 0.2063% | % | 8727272.7273 | 18000 | -18000
INTEREST - 15 MONTHS (BUILD, SETTLEMENT) - 8.39% Pa | 6.795% | % | 8727272.7273 | 593036.7551 | -593036.7551
MONTHLY BAS FOR GST | 13 | Mths | 500 | 6500 | -6500
SUBTOTAL | 8.847% | % | 8727272.7273 | 772108.5278 | -772108.5278 | 0
DEVELOPER TOTALS WITH FINANCE |  |  | IS THE INTEREST CAPITALISED (YES/NO or Y/N)? |  |  | NO
OFFICES & EXPENSES | 27 | Mths | 6166.7496 | 166502.2402 | -166502.2402
LAND PURCHASE COST + LAND STAMP DUTY + MISC FEES | 607 | m2 | 8369.4524 | 5080257.63 | -5080257.63
PURCHASE LOAN | 70% | % | 4808000 | 3365600 |  | 3365600
CDC + BUYER AGENT + SECTION 7.11 CONTRIBUTIONS | 4.752% | % | 4808000 | 228499.8 | -228499.8
PURCHASE FINANCE COST PAID | 13.3% | % | 3365600 | 447457.3368 | -447457.3368
RENTAL RETURN | 49 | Wks | 2082.5 | 102042.5 |  | 102042.5
SUBTOTAL - PURCHAST & PROPERTY DEVELOPMENT | 43.42% | % | 5654172.2668 | -2455074.507 | -5922717.007 | 3467642.5
LOAN AMOUNT | 75% | % | 11636363.6364 | 8727272.7273 |  | 8727272.7273
FINANCE FEES - PURCHASE + CONSTRUCTION | 1.271% | % | 8727272.7273 | 110935.4091 | -110935.4091
FINANCE INTEREST PURCHASE + CONSTRUCTION (CAPITIALISED) | 0% | % | 8727272.7273 | 0 | 0
PURCHASE LOAN REPAYMENT | 70% | % | 4808000 | 3365600 | -3365600
BUILD COST + CONSULTANTS + SERVICES + CONTINGENCY | 788.11 | m2 | 6966.8448 | 5490640.0598 | -5490640.0598
BUILDER INVESTMENT (CAPITALISED OR NOT - INTEREST) | 8.594% | % | 8727272.7273 | 750000 |  | 750000
INVESTMENT (CAPITALISED INTEREST) | 0% | % | 8727272.7273 | 0 |  | 0
SUBTOTAL - PRE-CONSTRUCTION (MUST NOT BE "-") | 5.688% | % | 8967175.4688 | 510097.2584 | -8967175.4688 | 9477272.7273
FINANCE INTEREST PURCHASE + CONSTRUCTION (NOT CAPITIALISED) | 7.576% | % | 8727272.7273 | 661173.1187 | -661173.1187
OFFSET ACCOUNT (INCL BUILDERS PROFIT | 13.72% | % | 8727272.7273 | 1197146.4698 |  | 1197146.4698
LAND TAX - YEAR 1 & 2 (1.6% PA) | 3.208% | % | 2530000 | 81160 | -81160
PLUS GST CREDIT (QS / LENDER / AGENT FEES | 9.091% | % | 461479.7977 | 41952.7089 |  | 41952.7089
SUBTOTAL - SERVICING DEBT | 5.692% | % | 8727272.7273 | 496766.0599 | -742333.1187 | 1239099.1786
SELL (INCL. GST) | 607 | m2 | 23798.0251 | 14445401.25 | 0 | 14445401.25
SELLING AGENT COMMISSION | 2% | % | 14445401.25 | 288908.025 | -288908.025
LESS GST PAYABLE - GST AT SETTLEMENT (MARGIN SCHEME) | 9.091% | % | 9637401.25 | 876127.3864 | -876127.3864
SUBTOTAL - SELLING COSTS | 8.065% | % | 14445401.25 | -1165035.4114 | -1165035.4114 | 0
LESS INVESTMENT (CAPITALISED INTEREST) | 0% | % | 8727272.7273 | 0 | 0
LESS INVESTMENT (CAPITALISED INTEREST) PROFIT | 10% | % | 0 | 0 | 0
LESS BUILDER PROFIT PAID POST SALE | 11.11% |  | 3864144.231 | 429349.359 | -429349.359
LESS BUILDER INVESTMENT | 61.12% | % | 1104349.359 | 675000 | -675000
LESS BUILDER INVESTMENT PROFIT | 10% | % | 750000 | 75000 | -75000
LESS DEVELOPER COST RECOVERY | 100% | % | 1281708.9485 | 1281708.9485 | -1281708.9485
LESS LOAN REPAYMENT | 75% | % | 11636363.6364 | 8727272.7273 | -8727272.7273
SUBTOTAL - COST RECOVERY | 77.45% | % | 14445401.25 | -11188331.0348 | -11188331.0348 | 0
DEVELOPER PROFIT (EXCL DEVELOPER INVESTMENT) | 50.23% | % | 1281708.9485 | 643823.6151 | -27985592.0408 | 28629415.6559
JOHINKE DEVELOPMENTS PROFIT (ROI) PRE TAX WITH FINANCE | ROI | % | 1448211.1887 | 643823.6151 | 44.46% | 22.23%
BUILDER PROFIT (ROI) PRE TAX WITH FINANCE | ROI | % | 1179349.359 | 504349.359 | 42.77% | 42.77%
INVESTOR PROFIT (ROI) PRE TAX FINANCE | ROI | % | 0 | 0 | N/A | N/A
DEVELOPER INCOME LESS TRUST TAX
JOHINKE PROJECTS DISTRIBUTION | 117 | Wks | 5502.7659 | 643823.6151 |  | 643823.6151
JOHINKE PROJECTS TAX | 25% | % | 643823.6151 | 160955.9038 | -160955.9038
SUBTOTAL POST TAX | 117 | Wks | 4127.0745 | 482867.7114 | -160955.9038 | 643823.6151
JOHINKE DEVELOPMENTS PROFIT (ROI) POST TAX | TAX | % | 1448211.1887 | 482867.7114 | 33.34% | 16.67%
BUILDER INCOME LESS INCOME TAX
BUILDER INCOME | 61 | Wks | 8268.0223 | 504349.359 |  | 504349.359
BUILDER INCOME TAX | 25% | % | 504349.359 | 126087.3397 | -126087.3397
SUBTOTAL POST TAX | 61 | Wks | 6201.0167 | 378262.0193 | -126087.3397 | 504349.359
BUILDER PROFIT (ROI) POST TAX | VARIES | % | 1179349.359 | 378262.0193 | 32.07% | 32.07%
DEVELOPMENT PROFIT VS OPPORTUNITY COST
LESS OPPORTUNITY COST - YEAR 1 - LESS TAX | 15% | % | 2390614.7668 | 358592.215 | -358592.215
LESS OPPORTUNITY COST - YEAR 2 - LESS TAX | 15% | % | 1179349.359 | 176902.4038 | -176902.4038
OPPORTUNITY COST - TAX CREDIT | 40.68% | % | 535494.6189 | 217820.4709 |  | 217820.4709
PROFIT | 44.46% | % | 1448211.1887 | 643823.6151 |  | 643823.6151
LESS PROFIT TAX | 25% | % | 643823.6151 | 160955.9038 | -160955.9038
SUBTOTAL | 11.41% | % | 1448211.1887 | 165193.5633 | -696450.5227 | 861644.086
SALE PRIOR TO CONSTRUCTION
COST TO DATE | 607 | m2 | 9314.9461 | 5654172.2668 | -5654172.2668
PURCHASE OFFER | 607 | m2 | 8319.6046 | 5050000 |  | 5050000
SUBTOTAL (LOSS) | 10.69% | % | 5654172.2668 | 604172.2668 | -604172.2668
BREAK EVEN SALE POINT (WORST CASE)
TOWNHOUSE A - MAR 2024 - Estimate - Internal Area | 306 | m2 | 21906.4716 | 6703380.317 |  | 6703380.317
TOWNHOUSE B - MAR 2024 - Estimate - Internal Area | 301 | m2 | 21906.4716 | 6593847.9589 |  | 6593847.9589
SUBTOTAL | 607 | m2 | 21906.4716 | 13297228.2759 |  | 13297228.2759
JOHINKE DEVELOPMENT RETURN | 0% | % | 1448211.1887 | 0 |  | 0
BUILDER PROFIT RETURN | 0% | % | 1179349.359 | 0 |  | 0
VARIANCE FROM BREAK EVEN | 0% | % | 2627560.5477 | 0 |  | 0
VARIANCE FROM ADJUSTED VALUATION | 0% | % | 2627560.5477 | 0 | -1148172.9741
7%
TOWNHOUSE A - MAR 2024 - Estimate - Internal Area | 306 | m2 | 23798.0251 | 7282195.6878 |  | 7282195.6878
TOWNHOUSE B - MAR 2024 - Estimate - Internal Area | 301 | m2 | 23798.0251 | 7163205.5622 |  | 7163205.5622
SUBTOTAL | 607 | m2 | 23798.0251 | 14445401.25 |  | 14445401.25
JOHINKE DEVELOPMENT RETURN | 44.46% | % | 1448211.1887 | 643823.6151 |  | 643823.6151
BUILDER PROFIT RETURN | 42.77% | % | 1179349.359 | 504349.359 |  | 504349.359
VARIANCE FROM BREAK EVEN | 43.7% | % | 2627560.5477 | 1148172.9741 |  | 1148172.9741
VARIANCE FROM ADJUSTED VALUATION | 0% | % | 2627560.5477 | 0 |  | 0
7%
TOWNHOUSE A - MAR 2024 - Estimate - Internal Area | 306 | m2 | 23912.1521 | 7317118.5291 |  | 7317118.5291
TOWNHOUSE B - MAR 2024 - Estimate - Internal Area | 301 | m2 | 23912.1521 | 7197557.7688 |  | 7197557.7688
SUBTOTAL | 607 | m2 | 23912.1521 | 14514676.2979 |  | 14514676.2979
JOHINKE DEVELOPMENT RETURN | 46.81% | % | 1448211.1887 | 677881.8844 |  | 677881.8844
BUILDER PROFIT RETURN | 45.03% | % | 1179349.359 | 531029.4401 |  | 531029.4401
VARIANCE FROM BREAK EVEN | 46.01% | % | 2627560.5477 | 1208911.3245 |  | 1208911.3245
VARIANCE FROM ADJUSTED VALUATION | 2.312% | % | 2627560.5477 | 60738.3503 |  | 60738.3503
7%
TOWNHOUSE A - MAR 2024 - Estimate - Internal Area | 306 | m2 | 23855.0886 | 7299657.1084 |  | 7299657.1084
TOWNHOUSE B - MAR 2024 - Estimate - Internal Area | 301 | m2 | 23855.0886 | 7180381.6655 |  | 7180381.6655
SUBTOTAL | 607 | m2 | 23855.0886 | 14480038.7739 |  | 14480038.7739
JOHINKE DEVELOPMENT RETURN | 45.63% | % | 1448211.1887 | 660820.5586 |  | 660820.5586
BUILDER PROFIT RETURN | 43.89% | % | 1179349.359 | 517664.1821 |  | 517664.1821
VARIANCE FROM BREAK EVEN | 44.85% | % | 2627560.5477 | 1178484.7407 |  | 1178484.7407
VARIANCE FROM ADJUSTED VALUATION | 1.154% | % | 2627560.5477 | 30311.7665 |  | 30311.7665

## INTEREST STUDY
3 Nield Avenue Balgowlah - Build Interest Cash Flow | [31 empty] | 2025-07-04 | 13
DESCRIPTION | QTY | UNIT | RATE | SUBTOTAL | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[5 empty] | 2024-08-01 | 2024-09-02 | 2024-10-04 | 2024-11-05 | 2024-12-07 | 2025-01-08 | 2025-02-09 | 2025-03-13 | 2025-04-14 | 2025-05-16 | 2025-06-17 | 2025-07-19 | 2025-08-20 | 2025-09-21 | 2025-10-23 | 2025-11-24 | 2025-12-26 | 2026-01-27 | 2026-02-28 | 2026-04-01 | 2026-04-29 | 2026-05-31 | 2026-07-02 | 2026-08-03 | 2026-09-04 | 2026-10-06 | 2026-11-07 | 2026-12-09
|  | UNIT | RATE | SUBTOTAL | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 30 | 31 | 30 | 31 | SUBTOTALS
ORIGINAL CDC
DEVELOPER PURCHASE FINANCE
INITIAL LOAN | 70% | % | 4808000 | 3365600
CDC PROGRAM |  |  | 13 |  | 2024-08-01: 7; 2025-03-13: SELLING PERIOD; 2025-05-16: FINANCE; 2025-06-17: FINANCE; 2025-07-19: LOT VACANT; 2025-08-20: LOT VACANT; 2025-09-21: LOT VACANT
APPLICATION FEE RATE + GST | 1.25% | % | 3365600 | 42070 | 2024-08-01: 42070 | 42070
MANDATE FEE + BROKERS COMM. + GST | 1.8% | % | 3365600 | 60580.8 | 2024-08-01: 60580.8 | 60580.8
LAWYERS FEE | 1 | LS | 3628.47 | 3628.47 | 2024-08-01: 3628.47 | 3628.47
MONTHLY ACCOUNT FEE | 14 | MTH | 100 | 1400 | 2024-08-01: 100; 2024-09-02: 100; 2024-10-04: 100; 2024-11-05: 100; 2024-12-07: 100; 2025-01-08: 100; 2025-02-09: 100; 2025-03-13: 100; 2025-04-14: 100; 2025-05-16: 100; 2025-06-17: 100; 2025-07-19: 100; 2025-08-20: 100; 2025-09-21: 100 | 1400
PURCHASE INTEREST RATE (Pa) | 8.65% | YR |  |  | 2024-08-01: 0.7347%; 2024-09-02: 0.711%; 2024-10-04: 0.7347%; 2024-11-05: 0.711%; 2024-12-07: 0.7347%; 2025-01-08: 0.7347%; 2025-02-09: 0.6636%; 2025-03-13: 0.7347%; 2025-04-14: 0.711%; 2025-05-16: 0.7347%; 2025-06-17: 0.711%; 2025-07-19: 0.7347%; 2025-08-20: 0.7347%; 2025-09-21: 0.711% | 10.1%
PURCHASE INTEREST | 10.1% | % | 3365600 | 339778.0668 | 2024-08-01: 24725.634; 2024-09-02: 23928.0329; 2024-10-04: 24725.634; 2024-11-05: 23928.0329; 2024-12-07: 24725.634; 2025-01-08: 24725.634; 2025-02-09: 22332.8307; 2025-03-13: 24725.634; 2025-04-14: 23928.0329; 2025-05-16: 24725.634; 2025-06-17: 23928.0329; 2025-07-19: 24725.634; 2025-08-20: 24725.634; 2025-09-21: 23928.0329 | 339778.0668
PURCHASE FEE + INTEREST PAID | 13.3% | % | 3365600 | -447457.3368 | 131104.904 | 24028.0329 | 24825.634 | 24028.0329 | 24825.634 | 24825.634 | 22432.8307 | 24825.634 | 24028.0329 | 24825.634 | 24028.0329 | 24825.634 | 24825.634 | 24028.0329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447457.3368
DEVELOPER BALANCE LOAN
BUILD PROGRAM |  |  | 13 |  | 2025-10-23: 13; 2026-12-09: SETTLEMENT
MEASURE OF WORK |  |  | S-CURVE |  | 2025-10-23: 5%; 2025-11-24: 7%; 2025-12-26: 10%; 2026-01-27: 12%; 2026-02-28: 10%; 2026-04-01: 10%; 2026-04-29: 10%; 2026-05-31: 8%; 2026-07-02: 8%; 2026-08-03: 8%; 2026-09-04: 7%; 2026-10-06: 5%; 2026-11-07: 0%; 2026-12-09: 0% | 100%
DEVELOPMENT LOAN - MAX 75LVR + TIP-IN | 74.13% | % | 11772727.2727 | 8727272.7273 | 2025-10-23: #REF!; 2025-11-24: #REF!; 2025-12-26: #REF!; 2026-01-27: #REF!; 2026-02-28: #REF!; 2026-04-01: #REF!; 2026-04-29: #REF!; 2026-05-31: #REF!; 2026-07-02: #REF!; 2026-08-03: #REF!; 2026-09-04: #REF!; 2026-10-06: #REF!; 2026-11-07: #REF!; 2026-12-09: #REF! | #REF!
DEVELOPER BUILD FINANCE
LAWYERS + DISBURSTMENTS | 1 | LS | 1844.5 | 1844.5 | 2025-10-23: 1844.5
APPLICATION FEE RATE + GST | 1.25% | % | 8727272.7273 | 109090.9091 | 2025-10-23: 109090.9091 | 109090.9091
QS REPORT | 1 | LS | 4000 | 4000 | 2025-10-23: 4000 | 4000
MONTHLY QS FEE | 14 | MTH | 1000 | 14000 | 2025-10-23: 1000; 2025-11-24: 1000; 2025-12-26: 1000; 2026-01-27: 1000; 2026-02-28: 1000; 2026-04-01: 1000; 2026-04-29: 1000; 2026-05-31: 1000; 2026-07-02: 1000; 2026-08-03: 1000; 2026-09-04: 1000; 2026-10-06: 1000; 2026-11-07: 1000; 2026-12-09: 1000 | 14000
BROKERS COMM + GST | 0.5% | % | 8727272.7273 | 43636.3636 | 2025-10-23: 43636.3636 | 43636.3636
INTEREST RATE (Pa) - ASSUEMED | 8.14% | YR |  |  | 2025-10-23: 0.669%; 2025-11-24: 0.6913%; 2025-12-26: 0.669%; 2026-01-27: 0.6913%; 2026-02-28: 0.6913%; 2026-04-01: 0.6244%; 2026-04-29: 0.6913%; 2026-05-31: 0.669%; 2026-07-02: 0.6913%; 2026-08-03: 0.669%; 2026-09-04: 0.6913%; 2026-10-06: 0.669%; 2026-11-07: 0.6913%; 2026-12-09: 0.669% | 9.478%
BALANCE FEE | 1.271% | % | 8727272.7273 | 110935.4091 | 2025-10-23: 110935.4091; 2025-11-24: 0; 2025-12-26: 0; 2026-01-27: 0; 2026-02-28: 0; 2026-04-01: 0; 2026-04-29: 0; 2026-05-31: 0; 2026-07-02: 0; 2026-08-03: 0; 2026-09-04: 0; 2026-10-06: 0; 2026-11-07: 0; 2026-12-09: 0 | 110935.4091
BALANCE QS & BROKERAGE SERVICES | 0.7063% |  | 8727272.7273 | 61636.3636 | 2025-10-23: 48636.3636; 2025-11-24: 1000; 2025-12-26: 1000; 2026-01-27: 1000; 2026-02-28: 1000; 2026-04-01: 1000; 2026-04-29: 1000; 2026-05-31: 1000; 2026-07-02: 1000; 2026-08-03: 1000; 2026-09-04: 1000; 2026-10-06: 1000; 2026-11-07: 1000; 2026-12-09: 1000 | 61636.3636
PURCHASE INTEREST - BALANCE | 3.397% | % | 8727272.7273 | 296477.0871 | 2025-10-23: 0; 2025-11-24: 22517.2471; 2025-12-26: 23267.822; 2026-01-27: 22517.2471; 2026-02-28: 23267.822; 2026-04-01: 23267.822; 2026-04-29: 21016.0973; 2026-05-31: 23267.822; 2026-07-02: 22517.2471; 2026-08-03: 23267.822; 2026-09-04: 22517.2471; 2026-10-06: 23267.822; 2026-11-07: 22517.2471; 2026-12-09: 23267.822 | 296477.0871
BALANCE INTEREST | 3.398% | % | 8727272.7273 | 296559.668 | 2025-10-23: 0; 2025-11-24: 2578.9354; 2025-12-26: 5322.0388; 2026-01-27: 8823.8239; 2026-02-28: 13673.0466; 2026-04-01: 17468.9592; 2026-04-29: 19206.981; 2026-05-31: 25060.7845; 2026-07-02: 27191.1431; 2026-08-03: 31134.2447; 2026-09-04: 33068.6853; 2026-10-06: 36828.1136; 2026-11-07: 37476.8419; 2026-12-09: 38726.07 | 296559.668
BALANCE LINE FEE RATE | 0% | YR | [30 empty] | 0 | bar: 2025-10-23 to 2026-12-09
BALANCE LINE FEE AMOUNT | 0% | % | 8727272.7273 | 0 | 2025-10-23: 0; 2025-11-24: 0; 2025-12-26: 0; 2026-01-27: 0; 2026-02-28: 0; 2026-04-01: 0; 2026-04-29: 0; 2026-05-31: 0; 2026-07-02: 0; 2026-08-03: 0; 2026-09-04: 0; 2026-10-06: 0; 2026-11-07: 0; 2026-12-09: 0 | 0
BALANCE INTEREST + FEE + LINE | 8.773% | % | 8727272.7273 | -765608.5278 | 2025-10-23: 159571.7727; 2025-11-24: 26096.1825; 2025-12-26: 29589.8608; 2026-01-27: 32341.0711; 2026-02-28: 37940.8686; 2026-04-01: 41736.7812; 2026-04-29: 41223.0783; 2026-05-31: 49328.6065; 2026-07-02: 50708.3903; 2026-08-03: 55402.0667; 2026-09-04: 56585.9324; 2026-10-06: 61095.9357; 2026-11-07: 60994.089; 2026-12-09: 62993.892 | 765608.5278
OFFSET ACCOUNT CALCULATION (INCL GST)
BUILD CLAIM | 100% | % | 5490640.0598 | 5490640.0598 | 2025-10-23: 0; 2025-11-24: 274532.003; 2025-12-26: 384344.8042; 2026-01-27: 549064.006; 2026-02-28: 658876.8072; 2026-04-01: 549064.006; 2026-04-29: 549064.006; 2026-05-31: 549064.006; 2026-07-02: 439251.2048; 2026-08-03: 439251.2048; 2026-09-04: 439251.2048; 2026-10-06: 384344.8042; 2026-11-07: 274532.003; 2026-12-09: 0 | 5490640.0598
PROFIT | 0% | % | 5490640.0598 | 0 | 2025-10-23: 0; 2025-11-24: 0; 2025-12-26: 0; 2026-01-27: 0; 2026-02-28: 0; 2026-04-01: 0; 2026-04-29: 0; 2026-05-31: 0; 2026-07-02: 0; 2026-08-03: 0; 2026-09-04: 0; 2026-10-06: 0; 2026-11-07: 0; 2026-12-09: 0 | 0
CONTINGENCY USED FOR VARIATIONS | 0% | % | 5490640.0598 | 0 | 2025-10-23: 0; 2025-11-24: 0; 2025-12-26: 0; 2026-01-27: 0; 2026-02-28: 0; 2026-04-01: 0; 2026-04-29: 0; 2026-05-31: 0; 2026-07-02: 0; 2026-08-03: 0; 2026-09-04: 0; 2026-10-06: 0; 2026-11-07: 0; 2026-12-09: 0 | 0
GST | 0% | % | 5490640.0598 | 0 | 2025-10-23: 0; 2025-11-24: 0; 2025-12-26: 0; 2026-01-27: 0; 2026-02-28: 0; 2026-04-01: 0; 2026-04-29: 0; 2026-05-31: 0; 2026-07-02: 0; 2026-08-03: 0; 2026-09-04: 0; 2026-10-06: 0; 2026-11-07: 0; 2026-12-09: 0 | 0
SUBTOTAL - BUILD CLAIM | 100% | % | 5490640.0598 | 5490640.0598 | 2025-10-23: 0; 2025-11-24: 274532.003; 2025-12-26: 384344.8042; 2026-01-27: 549064.006; 2026-02-28: 658876.8072; 2026-04-01: 549064.006; 2026-04-29: 549064.006; 2026-05-31: 549064.006; 2026-07-02: 439251.2048; 2026-08-03: 439251.2048; 2026-09-04: 439251.2048; 2026-10-06: 384344.8042; 2026-11-07: 274532.003; 2026-12-09: 0 | 5490640.0598
ACTUAL CLAIM WITH VARIATIONS (CONSULT + SERVICES) | 90% | % | 4293493.59 | 3864144.231 | 2025-10-23: 0; 2025-11-24: 193207.2116; 2025-12-26: 270490.0962; 2026-01-27: 386414.4231; 2026-02-28: 463697.3077; 2026-04-01: 386414.4231; 2026-04-29: 386414.4231; 2026-05-31: 386414.4231; 2026-07-02: 309131.5385; 2026-08-03: 309131.5385; 2026-09-04: 309131.5385; 2026-10-06: 270490.0962; 2026-11-07: 193207.2116; 2026-12-09: 0 | 3864144.231
CONTINGENCY USED FOR VARIATIONS | 0% | % | 4293493.59 | 0 | 2025-10-23: 0; 2025-11-24: 0; 2025-12-26: 0; 2026-01-27: 0; 2026-02-28: 0; 2026-04-01: 0; 2026-04-29: 0; 2026-05-31: 0; 2026-07-02: 0; 2026-08-03: 0; 2026-09-04: 0; 2026-10-06: 0; 2026-11-07: 0; 2026-12-09: 0 | 0
PROFIT | 10% | % | 4293493.59 | 429349.359 | 2025-10-23: 0; 2025-11-24: 21467.468; 2025-12-26: 30054.4551; 2026-01-27: 42934.9359; 2026-02-28: 51521.9231; 2026-04-01: 42934.9359; 2026-04-29: 42934.9359; 2026-05-31: 42934.9359; 2026-07-02: 34347.9487; 2026-08-03: 34347.9487; 2026-09-04: 34347.9487; 2026-10-06: 30054.4551; 2026-11-07: 21467.468; 2026-12-09: 0 | 429349.359
GST | 0% | % | 4293493.59 | 0 | 2025-10-23: 0; 2025-11-24: 0; 2025-12-26: 0; 2026-01-27: 0; 2026-02-28: 0; 2026-04-01: 0; 2026-04-29: 0; 2026-05-31: 0; 2026-07-02: 0; 2026-08-03: 0; 2026-09-04: 0; 2026-10-06: 0; 2026-11-07: 0; 2026-12-09: 0 | 0
SUBTOTAL - ACTUAL CLAIM | 100% |  | 4293493.59 | 4293493.59 | 2025-10-23: 0; 2025-11-24: 214674.6795; 2025-12-26: 300544.5513; 2026-01-27: 429349.359; 2026-02-28: 515219.2308; 2026-04-01: 429349.359; 2026-04-29: 429349.359; 2026-05-31: 429349.359; 2026-07-02: 343479.4872; 2026-08-03: 343479.4872; 2026-09-04: 343479.4872; 2026-10-06: 300544.5513; 2026-11-07: 214674.6795; 2026-12-09: 0 | 4293493.59
TOTAL OFFSET ACCOUNT | 21.8% | % | 5490640.0598 | 1197146.4698 | 2025-10-23: 0; 2025-11-24: 59857.3235; 2025-12-26: 83800.2529; 2026-01-27: 119714.647; 2026-02-28: 143657.5764; 2026-04-01: 119714.647; 2026-04-29: 119714.647; 2026-05-31: 119714.647; 2026-07-02: 95771.7176; 2026-08-03: 95771.7176; 2026-09-04: 95771.7176; 2026-10-06: 83800.2529; 2026-11-07: 59857.3235; 2026-12-09: 0 | 1197146.4698
DEVELOPER FINANCE | INTEREST CAPITALISED? (YES / NO) |  |  | NO
DEVELOPMENT LOAN (INCL CONTINGENCY) | 100% | % | 8727272.7273 | 8727272.7273
ESTABLISHMENT FEES | 1.271% | % | 8727272.7273 | -110935.4091
PURCHASE LOAN AMOUNT | 38.56% | % | 8727272.7273 | -3365600
BUILDING LOAN AMOUNT | 62.91% | % | 8727272.7273 | -5490640.0598
INTEREST REPAYMENTS | 0% | % | 8727272.7273 | 0
DEVELOPER INVESTMENT | 8.594% | % | 8727272.7273 | 750000
BALANCE AMOUNT | 2.749% | % | 8727272.7273 | 239902.7416
BALANCED CHECK |  |  | 8727272.7273 | ERROR
$4,173,493.59 + GST
10000

## PROPOSED LOAN
FINANCIAL LENDING
Loan Requirements
Loan Amount | A | 8727273 |  | Residential/Commercial |  |  | Residential
Application Fee (%) |  | 1.25% |  | State |  |  | NSW
Referral Fee (%) |  | 0.5% |  | Number of Securities |  |  | 1
Referral Fee($) | B | 43636.365 |  | Title Insurance |  |  | Refer to First Title
For Increases only - Original Loan Amount
Is this application an Internal Refinance? |  | No
Funds Required |  |  |  | Funds Available
Application Fee | C | 109090.9125 |  | Loan Approved |  | A | 8727273
Title Insurance |  | Refer to First Title |  | Deposit Paid (Land Only) Savings
Disbursement and Electronic Filing Fee | D | 300 |  | Gifted Funds
Lenders Legal | E | 544.5 |  | FHOG
Solicitors Out of Pockets GSA Fee | F | 1000
General Security Agreement Fee
Brokerage/ Mandate (if applicable)
Purchase Price
Stamp Duty
GST on purchase (if applicable)
Outgoing Financial Institute Mortgage Refinance (including exit fees) | G | 3365600
Debt Consolidation
Construction / Check Cost (higher of) | H | 5717000
Other Construction Costs (To be retained)
Interest Budget (to be retained)
Other Construction Costs (Applicant to pay)
Contingencies | I | 285850
Total funds required | J | 9479385.4125 |  | Total resources available s,11s,ooo.oo 1 |  | A | 8727273
Construction Funding Breakdown
Loan Breakdown |  |  |  | Loan to Cost Table
On Completion Value | K | 11772727.2727 |  | Land Value |  | L | 4000000
Land (Valuation) | L | 4000000 |  | Build Costs |  | H | 5717000
Loan | A | 8727273 |  | Contingency |  | I | 285850
[5 empty] | Interest Already Paid | T | 300000
LVR Breakdown |  |  |  |  | Interest Budget Retainined |  | 0
LVR at Land (max 66.66%) |  | 45.83% | A / L |  | Acquisition Costs |  | 0
LVR on Completion (At time of Valuation) |  | 74.13% | A / K |  | Stamp Duty Already Paid | U | 240000
Loan to Cost (max 80%) |  | 80% | A / Z |  | Selling Costs | V | 256000
Net Equity on Completion | M | 3045454.2727 |  |  | Statutory Charges | W | 1000
[5 empty] | Loan Setup / Application Fee | C | 109090.9125
Funds Disbursement |  |  |  |  | Open Space Contributions
Disbursement for Settlement Fees | N | 110935.4125 | SUM(C : F) | Build related costs |  | Y | 6908940.9125 | SUM(H : C)
Purchase/refinance/cash outlay | O | 2613487.5875 | A - N - Q - R | Total Costs for Loan to Cost Ratio |  | Z | 10908940.9125 | Y + L
Advance at settlement: | P | 2724423 | N + O
Applicants contribution at settlement | Q | -752112.4125 | A - J
Funds held for Construction | R | 6002850 | I + H
Contingency set aside | I | 285850
Funds available to builder | H | 5717000
Applicants contribution towards Construction |  | Not Required | • Release of deposit at settlement will bereviewed on a case by case basis, refer to COT if required.
Equity Release at Frame Stage | S | 0
Funding breakdown guide:
Settlement/Construction funding condition
Shortfall of funds condition
Equity release at frame condition
Version 1.9

## VISUALISATION
3 Nield Avenue Balgowlah - Visualisation
VISUAL REPRESENTATION | AMOUT | DESCRIPTION
| 166502.2402 | Offices & Expenses
| 4808000 | Purchase Cost
| 5080257.63 | Purchase + Stamp Duty Cost
PURCHASE | 3365600 | Purchase Loan Credits
| 228499.8 | CDC + Council Fees Cost
| 447457.3368 | Interest & Fees Cost
| 102042.5 | Rental Income
DEVELOPMENT | -2455074.507 | Subtotal Purchase & Development Cost
| 5490640.0598 | = $5,712,000 Inflatered Build LESS $285,000 Contingency Cost LESS GST
| 3365600 | Purchase Loan Cost
| Loan-to-Cost | Max Loan Metics - Loan to Value 75.00%(LVR), Loan to Cost 80.00% (LtC) & Loan-to-Land 66.66%(LtL)
| 8727272.7273 | 750000
| 110935.4091 | Fees
| 750000 | Builder Investment
FINANCE | 510097.2584 | Subtotal Pre-Construction
| 1239099.1786 | 4293493.59
| 661173.1187 | QS Services & Interest Cost
| 81160 | Land Tax Cost - Year 1 & 2
| 41952.7089 | GST Credits for QS / Lender / Agent Fees
SERVICE | 496766.0599 | Subtotal - Servicability
| 12950000 | JLL Property Under Valuation 05-May-2025
| 13500375 | Mark Valuation Adjustment 05-May-2025
SALE | 14445401.25 | Subtotal Mark Valuation - 25-Oct-2025 - 18 Months Post Valuation (5 rate drops - 7.5% increase)
| 288908.025 | Selling Agent Fee
| 876127.3864 | GST Margin Scheme with
| 1179349.359 | Profit (10% Build) + Investment Recovery + Investment Profit (10%)
| 1281708.9485 | Developer Profit + Investment Recovery + Investment Profit (10%)
| 8727272.7273 | Loan Repayment Cost
COST RECOVERY | -12353366.4462 | Subtotal Fees & Cost Recovery + Loan Repayment
44.46% | 643823.6151 | Total Profit Pre Tax
33.34% | 482867.7114 | Total Profit Post Tax (Corporate Beneficiery)